## Ark1
| PLAN |  |  |  |  | DESIGN |  |  |  |  | BUILD |  |  |  |  | BUILD |  |  |  |  | TEST/LAUNCH |  |  |  |  | REPORT
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30
Jørgen | Create Project Plan
Jørgen | Identify the key dependencies and goals
Jørgen |  | Identifying the Required Resources
Jørgen |  |  | Constructing a Project Schedule
Jørgen |  |  |  | Create Milestones
Jørgen |  |  | Identifying the Critical Path and Critical Tasks
Jørgen |  |  |  | Modify the Project Schedule
Jørgen |  |  |  | Create Functional Specification Document
Jørgen | [5 empty] | Find the target audience
Jørgen | [5 empty] | Make research on Microsites
Jørgen | [6 empty] | Create Personas
Jørgen | [6 empty] | Choose relevant API
Jørgen | [7 empty] | Create wireframes
Jørgen | [7 empty] | Create color color pallette
Jørgen | [7 empty] | Select typography
Jørgen | [7 empty] | Select UI elements
Jørgen | [8 empty] | Create Prototypes
Jørgen | [10 empty] | Create HTML layouts
Jørgen | [10 empty] | Write CSS base content
Jørgen | [10 empty] | Create CSS responsive layout
Jørgen | [10 empty] | Create HTML Modules and justify with CSS
Jørgen | [11 empty] | Fetch content from API's
Jørgen | [11 empty] | Create Elements with JS to the HTML modules
Jørgen | [11 empty] | Append children to the elements using JS
Jørgen | [15 empty] | Modify the pages with CSS
Jørgen | [20 empty] | Using various tools check if SEO / Content Strategy / WCAG is achieved
Jørgen | [21 empty] | Test the mobile friendliness
Jørgen | [21 empty] | Make adjustments
Jørgen | [25 empty] | Write the report