## Phase
Work Breakdown Structure (WBS)
Phase Title | Phase Description | Phase Sequence
List Phase titles (eg: Initiation, Planning, Execution, Closure and Evaluation). | Describe the purpose and key outcomes of each Phase | Number each Phase in sequence
Planning | Manage project scope and determine solutions for the problems. | 1
Systems Analysis and Requirements | Analyzing the needs of the end users and functional requirements of the solutions | 2
Systems Design |  | 3
Development |  | 4
Integration and Testing |  | 5
Implementation |  | 6
Operations and Maintenance |  | 7

## Activity
Phase Title | Activity Title | Activity Description | Activity Sequence
List the phase that the Activity corresponds to. | List the title of each Activity. | Describe the purpose and outcomes of each Activity. | Number each Activity in sequence.
Planning | Create a Project Plan | Defining the Work Breakdown Structure | 1
| Create Milestones | Check how the project is progressing | 2
| Identifying the Required Resources | Construct a Resource Plan | 3
| Constructing a Project Schedule | Create a Gantt chart with milestones, activities, durations etc. | 4
| Dependencies | Identify any key dependencies in the Project Schedule | 5
| Identifying the Critical Path and Critical Tasks | Figure out if any tasks delay the whole project | 6
| Modifying a Project Schedule |  | 7
Systems Analysis and Requirements | Get Oriented |  | 8
| Discover the Primary Business Objectives |  | 9
| Define Scope |  | 10
| Formulate Your Business Analysis Plan | Create Functional Specification Document | 11
| Define the Detailed Requirements | Create Functional Specification Document | 12
| Support the Technical Implementation | Create Functional Specification Document | 13
| Help the Business Implement the Solution | Create Functional Specification Document | 14
| Assess Value Created by the Solution | Create Functional Specification Document | 15
User Experience | Find out who the target audience are |  | 16
| Make research | Study different Microsites | 17
| Create personas | Based on potential painpoints, user goals | 18
| Choose relevant API | Choose relevant material | 19
UX/ UI | Wireframe | Create wireframes | 20
Design | Prototype | Include UI elements, colors and typography | 21
22
Programming | Create HTML layouts | Follow the sematcs rules and create a structure | 23
| Write all the CSS base content | Choose, font size, font -weight, colors, background, icons etc… | 24
| Create CSS responsive layout | Create CSS responcive tables | 25
| Create CSS modules | Create common reusable modules like boxes, navigations, and other child elements etc… | 26
| Fetch information content from API | Use the fetch method to extract material for each Microsite page | 27
| Manipulate with the DOM | Create Elements and append children with JS to the HTML modules | 28
Integration and Testing | Test Analysis Approval Determination | summarizes the system’s perceived readiness and is attached to the Test Analysis Report as a final result of the test reviews. | 29
| Test Problem Reports | document problems encountered during testing; are also attached to the Test Analysis Report. | 30
| Information Technology Systems Certification & Accreditation | includes completion of a Security Risk Assessment, Sensitive System Security Plan, Security Operating Procedures, Security Test and Evaluation, and Certification Statements. | 31
Implementation | Complete System | includes all code – modules, components, and libraries – kept in the production version of the data repository. | 32
| System Documentation | includes all technical documentation delivered during the project (e.g. the SDD and System Administration Manual). | 33
| Version Description Document | primary configuration control document used to track and control versions of a system released to the operational environment. It also summarizes features and contents for the build and identifies and describes the version delivered. | 34
| Post-Implementation Review Report | summarizes the assessment of Implementation activities at the end of the Implementation Phase | 35
| Standard Operating Procedures | defines in detail how the Systems Team will perform the business processes related to the operations and maintenance of the system. | 36
Operations and Maintenance | Standard Operating Procedures (Updated) |  | 37
| Implementation Notice | formally requests approval for system changes made during the Implementation Phase. | 38
| In-Process Review Report | formally reports the health of the system. It includes summary of performance reports but is more formalized and usually developed quarterly. | 39
| User Satisfaction Review | determines the current user satisfaction with the performance capabilities of the system. | 40
Report | Introduction/Interpretation of the assignment |  | 42
| Planning, functional spec, Gantt chart |  | 43
| Target audience/research |  | 44
| Graphic design: design principles, typography, color |  | 45
| HTML/CSS: Semantics, structure |  | 46
| SEO/Content Stategy/WCAG |  | 47
| Interface Design: Personae/Scenario, Affordances, Navigation, Persuasion, Wireframing, Prototyping |  | 48
| Javascript |  | 49
| Implementation/rollout |  | 50
| Conclusion |  | 51

## Task
Task Title | Task Title | Task Description | Task Sequence
List the phase that the Task corresponds to. | List the title of each Task. | Describe the purpose and outcomes of each Task. | Number each Task in sequence.
Planning | Create a Project Plan
Create Milestones
Identifying the Required Resources
Constructing a Project Schedule
Dependencies
Identifying the Critical Path and Critical Tasks
Modifying a Project Schedule
Systems Analysis and Requirements | Get Oriented
Discover the Primary Business Objectives
Define Scope
Formulate Your Business Analysis Plan
Define the Detailed Requirements
Support the Technical Implementation
Help the Business Implement the Solution
Assess Value Created by the Solution